## Breakdown
Epic | Feature | Page | User Story | Acceptance Criteria | FE (Days) | BE (Days) | DevOps (Days) | Design (Days) | Risks | Comments | Assumptions
Technical Setup | Environment Setup | N/A | Development Environment Setup | Development, staging, and production environments are configured with proper secrets management, environment variables, and deployment targets | 1 | 1.5 | 3 | 0 | Cloud provider configuration complexity and credential management | Includes Docker containerization, environment-specific configs, and local development setup | Using standard cloud provider (AWS/Azure/GCP) with managed services for database and hosting
Technical Setup | Environment Setup | N/A | CI/CD Pipeline Configuration | Automated build, test, and deployment pipeline with proper branching strategy, code quality gates, and deployment approvals | 0.5 | 0.5 | 2.5 | 0 | Pipeline complexity and integration with multiple environments | Includes automated testing, code coverage, security scanning, and deployment automation | Using GitHub Actions or similar CI/CD platform with standard deployment patterns
Technical Setup | Environment Setup | N/A | Database Schema and Knowledge Graph Setup | Database schema created with proper indexing, relationships, and knowledge graph structure for AI-powered search and recommendations | 0 | 3 | 1 | 0 | Knowledge graph complexity and performance optimization for large datasets | Includes user management, content storage, search indexing, and AI model integration schemas | Using PostgreSQL with vector extensions or similar for knowledge graph capabilities
Authentication | Azure AD Integration | Login | Azure AD SSO Login | User can authenticate via Azure AD SSO, redirected to dashboard on success, error handling for failed auth | 2 | 3 | 1 | 1 | Azure AD configuration complexity and tenant-specific requirements | Requires Azure AD app registration, MSAL.js integration, token handling | Azure AD tenant is already configured, standard enterprise SSO flow
Authentication | Azure AD Integration | N/A | User Session Management | Sessions persist across browser refresh, automatic logout on token expiry, secure token storage | 1.5 | 2 | 0.5 | 0 | Token refresh timing and secure storage implementation | JWT token management, refresh token flow, secure httpOnly cookies | Standard JWT token lifecycle, 8-hour session duration
Search & Discovery | Search Interface | Search Dashboard | Search Dashboard UI | User can access search dashboard with proper layout, navigation, and responsive design matching design tokens | 2 | 0 | 0 | 1.5 | Complex responsive layout requirements | Implement using design system components, ensure proper spacing and typography per design tokens | Design system components are already available, no complex animations required
Search & Discovery | Search Interface | Search Dashboard | Search Input and Validation | User can enter search queries with real-time validation, character limits, and proper error states | 1.5 | 0.5 | 0 | 0.5 | Input validation complexity and edge cases | Include debouncing for real-time validation, handle special characters and query length limits | Basic text input validation, no advanced query syntax parsing required
Search & Discovery | Search Interface | Search Dashboard | Search Filters Panel | User can apply multiple filters with clear/reset functionality, filter state persistence, and intuitive UI | 3 | 1 | 0 | 2 | Complex filter combinations and state management | Implement collapsible filter groups, multi-select options, date ranges, and filter chips | Maximum 8-10 filter types, standard filter UI patterns acceptable
Search & Discovery | Search Backend | N/A | Semantic Search API | API endpoint processes natural language queries and returns semantically relevant results with confidence scores | 0 | 4 | 0.5 | 0 | Integration complexity with vector database and ML models | Integrate with vector database, implement query preprocessing, result ranking algorithm | Using existing vector database service (e.g., Pinecone, Weaviate), pre-trained embeddings model available
Search & Discovery | Search Backend | N/A | Vector Embeddings and Indexing | Content is automatically converted to vector embeddings and indexed for semantic search with batch processing capability | 0 | 5 | 1 | 0 | Large-scale indexing performance and embedding model selection | Implement batch processing for embeddings generation, incremental indexing, embedding model management | Using cloud-based embedding service (OpenAI, Cohere), existing content database structure
Search & Discovery | Search Backend | N/A | Search Filtering Logic | Backend applies multiple filters to search results with proper boolean logic and performance optimization | 0 | 2.5 | 0 | 0 | Query performance with complex filter combinations | Implement efficient database queries, filter caching, query optimization for large datasets | Database supports complex filtering, reasonable dataset size (<1M records initially)
Search & Discovery | Search Results | Search Results | Search Results Display | Search results display with relevance scores, snippets, metadata, and proper loading/empty states | 2.5 | 1 | 0 | 1.5 | Result card layout complexity and performance with large result sets | Implement result cards with highlighting, metadata display, loading skeletons, empty states | Standard result card layout, text highlighting for search terms, basic metadata display
Search & Discovery | Search Results | Search Results | Relevance Scoring and Ranking | Results are ranked by relevance with configurable scoring algorithm and score transparency for users | 1 | 3 | 0 | 0.5 | Relevance algorithm accuracy and performance tuning | Implement hybrid scoring (semantic + keyword), result re-ranking, score normalization | Basic relevance scoring acceptable initially, no ML-based ranking required
Search & Discovery | Search Results | Search Results | Load More Results | Users can load additional results with pagination or infinite scroll, maintaining search context and performance | 1.5 | 1.5 | 0 | 0.5 | Performance degradation with large result sets and state management complexity | Implement cursor-based pagination, result caching, smooth loading transitions | Infinite scroll preferred over traditional pagination, reasonable page sizes (20-50 results)
AI Analysis | Relevance Analysis | Search Results | Similarities and Differences Analysis | Display AI-generated analysis comparing similarities and differences between search results and query context. Show analysis in expandable sections with clear visual hierarchy. | 3 | 2 | 0 | 1.5 | LLM response quality and consistency may vary significantly | Requires integration with LLM service and proper error handling for failed analysis. Consider caching analysis results. | LLM service is already selected and accessible via API
AI Analysis | Relevance Analysis | N/A | LLM Integration for Content Analysis | Integrate with LLM service to analyze memo content and generate relevance scores, similarities, and differences. Handle API failures gracefully with fallback messaging. | 0 | 4 | 1 | 0 | LLM API rate limits and costs could impact system performance | Need to implement prompt engineering, response parsing, and error handling. Consider implementing request queuing for rate limiting. | LLM service supports the required analysis capabilities and has sufficient rate limits
AI Analysis | Summarization | Memo Summary View | Memo Summary Generation | Generate AI-powered summaries of memo content including key points, main topics, and actionable items. Support different summary lengths (brief, detailed). | 0 | 3.5 | 0 | 0 | Summary quality may not meet user expectations for complex or technical memos | Requires careful prompt engineering to ensure consistent summary format. Need to handle very long memos that exceed LLM context limits. | LLM can process memo content within token limits and generate coherent summaries
AI Analysis | Summarization | Memo Summary View | Summary Display Interface | Display generated summaries with options to expand/collapse sections, regenerate summary, and provide feedback on summary quality. Include loading states and error handling. | 2.5 | 1 | 0 | 2 | Complex interaction patterns may confuse users if not designed intuitively | Need to implement progressive disclosure for different summary sections. Consider adding copy-to-clipboard functionality. | Summary data structure is well-defined and consistent from backend API
Memo Management | Memo Display | Memo Detail View | Memo Detail View | User can navigate to memo detail page, view memo in clean layout with proper navigation and responsive design | 2 | 0.5 | 0 | 1.5 | Complex layout requirements and responsive behavior across devices | Requires routing setup, page layout component, and integration with memo API. Consider print-friendly styling. | Memo ID is passed via URL parameter, basic memo structure is already defined
Memo Management | Memo Display | Memo Detail View | Memo Metadata Display | Display memo title, date, author, classification, distribution list, and other metadata in organized format | 1.5 | 1 | 0 | 1 | Metadata formatting complexity and handling missing/optional fields | Need to handle various metadata types, date formatting, and classification badges. Consider metadata edit permissions. | Metadata schema is well-defined, classification levels are predetermined
Memo Management | Memo Display | Memo Detail View | Memo Content Rendering | Render memo body content with proper formatting, handle rich text, images, tables, and maintain document structure | 3 | 1.5 | 0 | 1 | Rich text rendering complexity, security concerns with HTML content, performance with large documents | May need rich text editor component or markdown renderer. Consider content sanitization and XSS protection. | Content format is standardized (HTML/Markdown), no complex embedded media beyond images
Memo Management | Memo Data Management | N/A | Memo Content API | API endpoint to retrieve memo content by ID with proper error handling, caching, and performance optimization | 0 | 2.5 | 0 | 0 | Performance with large memo content, database query optimization, caching strategy | Include content versioning support, lazy loading for large documents, and proper error responses for missing memos. | Database schema supports memo storage, authentication/authorization is handled separately
Memo Management | Memo Data Management | N/A | Memo Metadata Management | API endpoints for memo metadata CRUD operations with validation, audit logging, and permission checks | 0 | 3 | 0 | 0 | Data validation complexity, audit trail requirements, permission matrix implementation | Include metadata validation rules, change tracking, and bulk operations support. Consider metadata templates. | User permission system exists, audit logging infrastructure is available
Memo Drafting | Draft Creation | Draft New Memo | Draft New Memo Interface | User can access draft memo page, see form fields for memo details, navigate between sections, and save draft progress | 3 | 1.5 | 0 | 2 | Complex form state management across multiple sections | Multi-step form with validation, auto-save functionality, responsive design for legal document creation | Form has 3-4 main sections, standard validation patterns, no complex conditional logic
Memo Drafting | Draft Creation | Draft New Memo | Template Selection | User can browse available memo templates, preview template structure, select template, and initialize new memo with template data | 2 | 1 | 0 | 1.5 | Template preview complexity and data structure variations | Template gallery with search/filter, preview modal, template metadata handling | 10-15 predefined templates, simple preview without full rendering, templates stored as structured data
Memo Drafting | Draft Creation | N/A | AI-Assisted Draft Generation | System generates memo content based on user inputs, provides AI suggestions for improvements, allows iterative refinement of generated content | 4 | 5 | 0.5 | 2.5 | AI service integration reliability and response time variability | Integration with AI service (OpenAI/similar), streaming responses, error handling for AI failures, content refinement UI | External AI API available, streaming responses supported, 5-10 second typical response time
Navigation & UX | Navigation | All Pages | Header Navigation | Header displays with logo, main navigation links, user menu, and search bar. Responsive behavior on mobile with hamburger menu. | 2 | 0.5 | 0 | 1 | Complex responsive behavior and mobile menu interactions | Needs to work across all pages. Consider sticky header behavior. Mobile menu requires JavaScript state management. | Design tokens are finalized. Navigation structure is stable. No complex mega-menu required.
Navigation & UX | Navigation | Detail Pages | Breadcrumb Navigation | Breadcrumb trail shows current page hierarchy. Clickable links to parent pages. Auto-generates based on route structure. | 1 | 0.5 | 0 | 0.5 | Dynamic breadcrumb generation complexity | Should integrate with routing system. Consider SEO structured data markup. | Route hierarchy is well-defined. No complex nested categories beyond 3-4 levels.
Navigation & UX | Navigation | All Pages | User Menu and Profile | User avatar/name in header opens dropdown menu. Menu includes profile, settings, logout options. Shows user role/permissions. | 1.5 | 1 | 0 | 0.5 | User session management and role-based menu items | Dropdown positioning and click-outside behavior. User avatar fallback for no profile image. | User authentication is implemented. Basic user profile data available via API.
Navigation & UX | Error Handling | Search Dashboard | Search Error Handling | Graceful handling of search API failures. User-friendly error messages. Retry mechanisms for transient failures. | 1 | 1.5 | 0 | 0.5 | Distinguishing between different error types and appropriate user messaging | Need error boundary components. Consider offline state handling. Log errors for monitoring. | Backend provides structured error responses. Error monitoring system exists.
Navigation & UX | Error Handling | All Content Pages | Content Loading Error States | Error states for failed content loads. Retry buttons where appropriate. Fallback content or navigation options. | 1.5 | 1 | 0 | 1 | Consistent error handling patterns across different content types | Reusable error components. Consider partial failure scenarios. Accessibility for error states. | Design system includes error state patterns. Backend provides consistent error format.
Navigation & UX | Error Handling | Search Results | Empty State Displays | Helpful empty states when no search results found. Suggestions for alternative searches. Clear messaging for different empty scenarios. | 1 | 0.5 | 0 | 1 | Providing meaningful guidance without overwhelming the user | Different empty states: no results, no filters match, initial state. Consider search suggestions. | Search analytics available to suggest alternatives. Content for empty state messaging provided.
Navigation & UX | Loading States | Search Dashboard | Search Loading States | Loading indicators during search execution. Progressive loading for large result sets. Skeleton screens for search results. | 1.5 | 0.5 | 0 | 1 | Performance perception during slow searches | Debounced search input. Skeleton components matching result card structure. Cancel previous requests. | Search API supports pagination. Design includes skeleton screen patterns.
Navigation & UX | Loading States | All Content Pages | Content Loading Indicators | Consistent loading indicators across application. Skeleton screens for content areas. Progress indicators for long operations. | 1 | 0 | 0 | 0.5 | Consistent loading experience across different content types | Reusable loading components. Consider lazy loading for images. Accessibility for loading states. | Design system includes loading patterns. Performance requirements defined for loading thresholds.
Data Management | Knowledge Graph | N/A | Memo Corpus Ingestion | System can ingest memo documents from various sources (upload, API, file system), extract text content, validate format, and store in processing queue with metadata | 0 | 3 | 0.5 | 0 | Document format variations and encoding issues may require additional parsing logic | Needs file upload handling, document parsing (PDF, DOCX, TXT), and queue management. Consider using libraries like Apache Tika for document parsing | Standard document formats only, no OCR required for scanned documents, reasonable file size limits (< 50MB per document)
Data Management | Knowledge Graph | N/A | Relationship Mapping | System analyzes memo content to identify and map relationships between entities (people, organizations, topics), creates relationship graph with confidence scores | 0 | 5 | 0 | 0 | NLP accuracy for entity recognition and relationship extraction may vary significantly across different memo types and writing styles | Requires NLP pipeline for named entity recognition, relationship extraction algorithms, and graph database integration. Consider using spaCy or similar NLP libraries | Using pre-trained NLP models, English language only, acceptable accuracy threshold of 80% for entity recognition
Data Management | Knowledge Graph | N/A | Content Indexing Pipeline | System creates searchable indexes of memo content, maintains full-text search capabilities, updates indexes incrementally as new content is added | 0 | 2.5 | 1 | 0 | Index performance may degrade with large document volumes, requiring optimization strategies | Implement using Elasticsearch or similar search engine, with incremental indexing and proper text analysis pipelines. Include stemming and synonym handling | Using managed search service (AWS OpenSearch/Elasticsearch), documents are primarily text-based, search response time under 500ms for typical queries
Testing & QA | Testing | N/A | End-to-End Testing Suite | Automated E2E tests cover critical user journeys including authentication, navigation, form submissions, and data operations with proper test data management | 3 | 1 | 2 | 0 | Test flakiness and maintenance overhead as application evolves | Use Playwright or Cypress. Include tests for responsive behavior and accessibility. Set up test data seeding and cleanup. | Testing framework choice is flexible, test environments are available, team has E2E testing experience
Testing & QA | Testing | N/A | API Testing and Validation | Comprehensive API test suite covering all endpoints with validation of request/response schemas, error handling, authentication, and edge cases | 0 | 2.5 | 1 | 0 | Incomplete coverage of edge cases and error scenarios | Use Jest/Supertest or similar. Include contract testing, rate limiting tests, and security validation. Mock external dependencies. | API documentation is complete, test database can be isolated, external service mocks are feasible
Testing & QA | Testing | N/A | Performance Testing | Load testing validates system performance under expected traffic with monitoring of response times, throughput, and resource utilization | 1 | 1.5 | 2.5 | 0 | Performance bottlenecks discovered late requiring architectural changes | Use k6 or Artillery for load testing. Include database performance monitoring. Test both API and frontend performance. | Performance requirements are defined, production-like test environment available, monitoring tools in place
|  |  | TOTALS |  | 52 | 76 | 18 | 26.5
|  |  | TOTAL DAYS |  | 172.5